## Sheet1
Member Name | Tasks Performed | Date | Hours Spent
All | Finalized app ideas, created power point for elevator pitch | 25/05/2016 | 1.5
| Final prep for elevator pitch, practice presentation | 26/05/2016 | 0.5
| Decided on technology stack for app, created a rough outline of milestones to accomplish, worked on first progress report | 2016-01-06 | 2
| Completed work on first progress report | 2016-02-06 | 2
| Decided on gameplay for the application | 2016-08-06 | 2
| Worked on progress presentation | 22/06/2016 | 2
| Worked on Progress Report 2 | 30/06/2016 | 3
Charlotte | Registered application with Fitbit. Looked into API authentication with OAuth 2.0 | 2016-09-06 | 0.75
| Made Java plugin for Unity to get response code from Fitbit | 22/06/2016 | 3
| Attempted to debug Auth code | 2016-05-07 | 5
| Worked on login screen UI | 2016-06-07 | 2
| Started player statistics class | 2016-12-07 | 5
| Began making UI for home screen | 13/07/2016 | 2
Darren | Worked on reward system and goals. | 2016-10-06 | 1
| Learning Unity | 23/06/2016 | 3
Denholm | Worked on boss fight logic | 2016-09-06 | 1
| Looked into Unity / menus | 2016-10-06 | 1
| UI workflow and prototype construction | 21/06/2016 | 3
| UI prototype finalization | 22/06/2016 | 2
| Unity research and development | 28/06/2016 | 2.5
| Started getting bosses to load from cache | 2016-05-07 | 3
| Troubleshooting configuration issues | 2016-07-07 | 4
| Fixed issues, got dynamic bosses working and finished boss UI | 2016-10-07 | 3
| Started building goal/challenge UI | 14/07/2016 | 8
| Dynamic loading of goals/challenges | 15/07/2016 | 8
| Fixing bugs, sprites, inconsistencies | 18/07/2016 | 4
| Presentation preparation | 20/07/2016 | 2
Evan | Set up AWS | 2016-04-06 | 4
| Implement Basic Server Code | 20/06/2016 | 4
| Rebase server code on Symfony | 27/06/2016 | 4
| Spin up RDS | 28/06/2016 | 1
| Update Server to Handle Users | 2016-04-07 | 4
| Begin OAUTH with fitbit | 2016-10-07 | 3
| Update DB Schema to better match Entites | 2016-11-07 | 4
| Finish OAUTH + User creation + Storage | 13/07/2016 | 5
| Worked on authentication/token storage and got app+server authentication working | 16/07/2016 | 5
| Worked on statelessness of the UNITY browser + added item manipulation | 16/07/2016 | 3
| Started the website | 19/07/2016 | 4
| Presentation preparation | 20/07/2016 | 2
| Continued work on website | 25/07/2016 | 2
| Finshed Website | 28/07/2016 | 2
Tyler | Added Initial project with minimal UI | 2016-12-06 | 1
| Added a toolbar to navigate the app | 21/06/2016 | 2
| Fixed Android build issues | 27/06/2016 | 2
| Added basic slots for inventory | 28/06/2016 | 3
| Got equipt items to load dynamically by adding Cache | 2016-05-07 | 5
| Add dynamic character sprite loading with Cache | 2016-06-07 | 1
| Add dynamic loading with items | 2016-07-07 | 3
| Fixed UI Rendering Issues | 13/07/2016 | 1
| Added dynamic sprite and Area choosing | 14/07/2016 | 3
| Added inventory dialogues and ability to equip and unequip items | 16/07/2016 | 8
| Worked on data integration between front end and middle ware | 17/07/2016 | 6
| Data integration | 18/07/2016 | 7
| Boss Gameplay | 19/07/2016 | 8
| Boss gameplay and inventory item persistence | 20/07/2016 | 8